## Burn Down Chart
Project: | Minesweeper
Sprint # | 5
[5 empty] | DATE: | 2023-06-19 | 2023-06-20 | 2023-06-21 | 2023-06-22 | 2023-06-23 | 2023-06-24 | 2023-06-25
| User Story ID | User Story | Task | Assigned To | Estimate (hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
| 16 | As a developer, I would like to have access to logs to better enhance the software and speed up the debugging process. | Implement logging features | Ryan and Raymond | 4 | 1 | 0 | 0.5 | 1 | 0.25 | 1 | 0.25
| 17 | As a developer, I would like to have page security to better protect the users. | Implement HTTP Request Filter in the form of page security. | Martin and Ryan | 3 | 0 | 1 | 0 | 0.4 | 1 | 0 | 0.6
| Ideal - Remaining efforts in uninterrupted working hours. |  |  |  | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0
| Actual - Remaining efforts in uninterrupted working hours. |  |  |  | 7 | 6 | 5 | 4.5 | 3.1 | 1.85 | 0.85 | 0

## Project Backlog
User Stories
ID | Feature | As a(n) <actor> | I would like to <description> | So that I can | Estimate (hours) | Assigned To | Sprint #
1 | Login Page | User | Login form with encryption | User info is secure | 1h | Raymond L. | 1
2 | Registration Page | User | User Registratin form | New users saved to database | 1h | Raymond L. | 1
3 | Login Handler | Developer | User input validation | Check database for user info | 1h | Raymond L. | 1
4 | Registration Handler | Developer | User info submission | Check if user info exists | 1h | Raymond L. | 1
5 | Game View | User | Gameboard that user can play | So that user can play the game as it should work | 1h | Martin C. | 2
6 | Game Models | Developer | All models needed to have a funtioing gamebaord | Have properties that can be saved and used to make the game work | 1h | Martin C. | 2
7 | Game Services | Developer | Develop the functionality of the game | This will give all the game all its features allowing it to be playable | 2h | Martin C. | 2
8 | Game DAO | Developer | Allow the game to communicate with the database | This allows the service to use a Database to save game board and its info | 1h | Martin C. | 2
9 | Game Tables | Developer | Create new tables to house info of the game itself | Allow for users to come back and finish old games | 1h | Martin C. | 2
10 | GameBoard Partial View | Developer | Create a Partial view that will house the gameboard | This will allow the game to return only the partial view with the use of ajax so that every time a cell is reveal the whole page does not have to load | 1h | Martin C. and Raymond L. | 3
11 | Add timestamps on main game view and partial view | Developer | When views are completed add date functions to display time | This will allow us to know the partial view is working correctly and that main game view is no reloading when not needed | 0.25h | Raymond L. | 3
12 | Add flag properties to model and update DB | User | Be able to flag cells we thing are bombs | This will the the user to flag cells, we will need to add the properties to the cell model and update BD to store new value | 1h | Martin And Ryan | 4
13 | Add Ajax to gameboard and write JS scripts for flad | Developer | Be able to flag a cell with right clicker and has ajax handle request with JS | This will allow us to have mutlieple mouse clicker event for revealing a cell and flagging a cell. Ajax will be used to hadle and return the partial view with jQuery. | 2h | Martin And Ryan | 4
14 | Update DAO and Services | Developer | update service and DAO to use new new properties correctly | Due to new properties being introduced to the model and new funtions being added the service and DAO has to be updated to have the methods needed and to make sure the correct properties are being sent to the DAO | 2h | Martin And Ryan | 4
15 | Create missing Diagrams | Developer | Create sitemap, UML, ER, Flow Diagrams | This will give the people looking at out game and report a better idea of how the project is working and what it took to get it to this point | 2h | Ryan and Raymond | 4
16 | Implement Logging | Developer | Have access to logs. | Better enhance the software and speed up the debugging process | 4h | Ryan and Raymond | 5
17 | HTTP Request Filter | Developer | Have page security | Protect the user more efficiently. | 3h | Martin and Ryan | 5

## How To Use
Step 1 | Hold a Sprint Planning meeting on Day 1 of of your Sprint where you will complete or update your User Stories as well as (re)prioritize your User Stories in your Product Back Log (ideally this should be done for the next 3-4 Sprints)
Step 2 | Copy the User Stories you plan to complete for this Sprint into your Sprint Back Log
Step 3 | Copy the User Stories you plan to complete from your Sprint Back Log into Column C
Step 4 | Break the User Story into a series of step by step development tasks in Column D
Step 5 | Estimate the User Story (in 1, 2, 4 or 8 Effort Man Hours) in Column F and if the task is larger than 8 hours break the User Story into multiple User Stories
Step 6 | Assign the User Story to a single Team Member in Column E
Step 7 | Repeat steps 4-6 for each User Story that has been planned for this Sprint
Step 8 | At the end of each day each Team Member should update the effort hours that were worked on their User Story to burn their work down
Step 9 | After each Daily Standup each Team Member should review the Burn Down Chart to ensure your Sprint will be delivered on time