## Burn Down Chart
Project: | Minesweeper
Sprint # | 2
[5 empty] | DATE: | 2023-05-15 | 2023-05-16 | 2023-05-17 | 2023-05-18 | 2023-05-19 | 2023-05-20 | 2023-05-21 | 2023-05-22 | 2023-05-23 | 2023-05-24
| User Story ID | User Story | Task | Assigned To | Estimate (hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 10
| 1 | I would like to be able to login and paly a game of minesweeper | Create game view | Marty | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | I would like to be able to come back and play a game I might not have been able to finish | Create table for the game so data can be stored. Tables will need to reference users so that game can be loaded again later on if needed. | Marty | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
| 3 | I would like to be able to play multiple games or start a new game whever I want | create a reset button and add funtionality so that the user can reset the game whenever they want | Marty | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
| 4 | I would like for the game to be playble | create basic funtion of the game at this moment so a basic minesweeper game can be played | Marty | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0
| 5 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 7 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 9 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 10 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ideal - Remaining efforts in uninterrupted working hours. |  |  |  | 7 | 6.3 | 5.6 | 4.9 | 4.2 | 3.5 | 2.8 | 2.1 | 1.4 | 0.7 | -1.1102e-15
| Actual - Remaining efforts in uninterrupted working hours. |  |  |  | 7 | 6 | 6 | 5 | 4 | 3 | 2 | 1 | 1 | 0 | 0

## Project Backlog
User Stories
ID | Feature | As a(n) <actor> | I would like to <description> | So that I can | Estimate (hours) | Assigned To | Sprint #
1 | Login Page | User | Login form with encryption | User info is secure | 1h | Raymond L. | 1
2 | Registration Page | User | User Registratin form | New users saved to database | 1h | Raymond L. | 1
3 | Login Handler | Developer | User input validation | Check database for user info | 1h | Raymond L. | 1
4 | Registration Handler | Developer | User info submission | Check if user info exists | 1h | Raymond L. | 1
5 | Game View | User | Gameboard that user can play | So that user can play the game as it should work | 1h | Martin C. | 2
6 | Game Models | Developer | All models needed to have a funtioing gamebaord | Have properties that can be saved and used to make the game work | 1h | Martin C. | 2
7 | Game Services | Developer | Develop the functionality of the game | This will give all the game all its features allowing it to be playable | 2h | Martin C. | 2
8 | Game DAO | Developer | Allow the game to communicate with the database | This allows the service to use a Database to save game board and its info | 1h | Martin C. | 2
9 | Game Tables | Developer | Create new tables to house info of the game itself | Allow for users to come back and finish old games | 1h | Martin C. | 2

## How To Use
Step 1 | Hold a Sprint Planning meeting on Day 1 of of your Sprint where you will complete or update your User Stories as well as (re)prioritize your User Stories in your Product Back Log (ideally this should be done for the next 3-4 Sprints)
Step 2 | Copy the User Stories you plan to complete for this Sprint into your Sprint Back Log
Step 3 | Copy the User Stories you plan to complete from your Sprint Back Log into Column C
Step 4 | Break the User Story into a series of step by step development tasks in Column D
Step 5 | Estimate the User Story (in 1, 2, 4 or 8 Effort Man Hours) in Column F and if the task is larger than 8 hours break the User Story into multiple User Stories
Step 6 | Assign the User Story to a single Team Member in Column E
Step 7 | Repeat steps 4-6 for each User Story that has been planned for this Sprint
Step 8 | At the end of each day each Team Member should update the effort hours that were worked on their User Story to burn their work down
Step 9 | After each Daily Standup each Team Member should review the Burn Down Chart to ensure your Sprint will be delivered on time